## Slide 1: Was the Project Really Late?
Presented by Tony Welsh, MA, MSc

## Slide 2: The best laid plans o’ mice an’ men gang aft a-gley.
(Robert Burns, 1759 – 1796)

## Slide 3
We all hear about how most projects are late, but late compared to what?
The planned project completion date is just a forecast.

## Slide 4
We all hear about how most projects are late, but late compared to what?
The planned project completion date is just a forecast.

## Slide 5
Perhaps our projects are
not “late.”
Perhaps our expectations are not reasonable.

## Slide 6
“Late chaotic projects are likely to be much later than the project manager thinks -- project completion isn’t three weeks away, it’s six months away. ….…, but that’s not a result of Brooks’ Law. It’s a result of underestimating the project in the first place."
(Steve McConnell, “Brooks' Law Repealed," IEEE Software, vol. 16, no. 6, Nov/Dec, 1999.)

## Slide 7
One reason this might be so is Merge Bias.

## Slide 8
“In these matters the only certainty is that nothing is certain.” (Pliny the Elder, 23 to 79 AD, Roman Naturalist.)
"Prediction is very difficult, especially if it's about the future." (Nils Bohr, 1885 to 1962)
“In these matters the only certainty is that nothing is certain.” (Pliny the Elder, 23 to 79 AD, Roman Naturalist.)
"Prediction is very difficult, especially if it's about the future." (Nils Bohr, 1885 to 1962)
“In these matters the only certainty is that nothing is certain.” (Pliny the Elder, 23 to 79 AD, Roman Naturalist.)
"Prediction is very difficult, especially if it's about the future." (Nils Bohr, 1885 to 1962)
“In these matters the only certainty is that nothing is certain.” (Pliny the Elder, 23 to 79 AD, Roman Naturalist.)
"Prediction is very difficult, especially if it's about the future." (Nils Bohr, 1885 to 1962)
“In these matters the only certainty is that nothing is certain.” (Pliny the Elder)

## Slide 9
“In these matters the only certainty is that nothing is certain.” (Pliny the Elder, 23 to 79 AD, Roman Naturalist.)
"Prediction is very difficult, especially if it's about the future." (Nils Bohr, 1885 to 1962)
“In these matters the only certainty is that nothing is certain.” (Pliny the Elder, 23 to 79 AD, Roman Naturalist.)
"Prediction is very difficult, especially if it's about the future." (Nils Bohr, 1885 to 1962)
“In these matters the only certainty is that nothing is certain.” (Pliny the Elder, 23 to 79 AD, Roman Naturalist.)
"Prediction is very difficult, especially if it's about the future." (Nils Bohr, 1885 to 1962)
“In these matters the only certainty is that nothing is certain.” (Pliny the Elder, 23 to 79 AD, Roman Naturalist.)
"Prediction is very difficult, especially if it's about the future." (Nils Bohr, 1885 to 1962)
“In these matters the only certainty is that nothing is certain.” (Pliny the Elder)
"Prediction is very difficult, especially if it's about the future." (Nils Bohr)

## Slide 10
Our estimate of project completion is just that, an estimate, and actual project completion is commonly assumed to be somewhere in a range of dates spread symmetrically around that estimate.

## Slide 11
But wait! It is much worse than that!

## Slide 12
But wait! It is much worse than that!
If the above were true, projects would be late only about half the time, and half the time they would be early.

## Slide 13
Maybe the deterministic estimate is not in the center of the likely range. Maybe it is not even within the range.

## Slide 14
Maybe the deterministic estimate is not in the center of the likely range. Maybe it is not even within the range.
In other words, maybe the estimate is biased.

## Slide 15
We are about to see that this is in fact the case for most project networks.

## Slide 16
We are about to see that this is in fact the case for most project networks.
We are about to meet Merge Bias.

## Slide 17
Consider a task which has just two predecessors which run in parallel. Suppose that each could take anything from 1 to 6 days with equal probability.
And suppose further that they will not take fractions of a day.

## Slide 18
We can simulate this with a pair of dice.

## Slide 19
We can simulate this with a pair of dice.
The expected value of one throw is 3.5, but what is the expected value of the best of two throws?

## Slide 20
Consider all possible outcomes:
 | 1 | 2 | 3 | 4 | 5 | 6
1 | 1 | 2 | 3 | 4 | 5 | 6
2 | 2 | 2 | 3 | 4 | 5 | 6
3 | 3 | 3 | 3 | 4 | 5 | 6
4 | 4 | 4 | 4 | 4 | 5 | 6
5 | 5 | 5 | 5 | 5 | 5 | 6
6 | 6 | 6 | 6 | 6 | 6 | 6

## Slide 21
If there are many things which could go wrong then at least one of them will.
If there are many things which could go wrong then at least one of them will.
If there are many things which could go wrong then at least one of them will.
If there are many things which could go wrong then at least one of them will.
Anything that can go wrong will go wrong.
(Murphy was a pessimist.)

## Slide 22
If there are many things which could go wrong then at least one of them will.
If there are many things which could go wrong then at least one of them will.
If there are many things which could go wrong then at least one of them will.
If there are many things which could go wrong then at least one of them will.
Anything that can go wrong will go wrong.
If there are many things which can go wrong then at least one of them probably will go wrong.

## Slide 23
Projects are generally more complicated than the two parallel tasks discussed before, and we cannot in general analyze the effects of uncertainty. So we simulate them.

## Slide 24
What is Monte Carlo simulation?

## Slide 25
In the context of a project network, Monte Carlo simulation:
1. Takes a sample from the user-defined distribution for each task duration;
2. Does a time analysis based on these sampled durations;
3. Stores the results of this time analysis (maybe in a summary form like a histogram);
4. Repeats steps 1 through 3 several hundred or thousand times.

## Slide 26
At the end of this process one has histograms representing the probability distributions of any calculated result of interest, which generally includes:
1. Early and late start and finish dates for all tasks;
2. Free and total floats for all tasks;
3. Costs for all tasks.

## Slide 27
That was a very simple example, but note that:
1. Merge bias builds up throughout the length of the project
2. There is no countervailing feature which tends to bias it the other way
3. Hence we might meet our early milestones, but become progressively later on subsequent milestones

## Slide 28
So, we should:
Stop beating ourselves up about late projects; and
Educate our stakeholders.

## Slide 29
Questions?